## Sheet1
Task | Owner | Start Date | End Date | Status | Duration
Conduct UX research | UX Lead | 2025-07-01 | 2025-07-04 | Not Started | 3
Create wireframes | Designer | 2025-07-05 | 2025-07-09 | Not Started | 4
Develop site | Dev Team | 2025-07-10 | 2025-07-19 | Not Started | 9
SEO review | SEO Specialist | 2025-07-20 | 2025-07-24 | Not Started | 4
Go live | PM | 2025-07-25 | 2025-07-26 | Not Started | 1