## Sheet1
Task | Owner | Start Date | End Date | Status | Duration
Define campaign goals | Marketing Lead | 2025-07-01 | 2025-07-02 | Not Started | 1
Design creatives | Designer | 2025-07-03 | 2025-07-05 | Not Started | 2
Build landing page | Web Dev | 2025-07-06 | 2025-07-09 | Not Started | 3
Launch ads | PPC Manager | 2025-07-10 | 2025-07-14 | Not Started | 4
Track conversions | Analytics Specialist | 2025-07-15 | 2025-07-30 | Not Started | 15