## Sheet1
Task | Owner | Start Date | End Date | Status | Duration
Gather requirements | Product Manager | 2025-07-01 | 2025-07-03 | Not Started | 2
Backend development | Backend Dev | 2025-07-04 | 2025-07-07 | Not Started | 3
Frontend integration | Frontend Dev | 2025-07-08 | 2025-07-13 | Not Started | 5
QA Testing | QA Engineer | 2025-07-14 | 2025-07-19 | Not Started | 5
Deploy to production | DevOps | 2025-07-20 | 2025-07-22 | Not Started | 2