## Sheet1
Task | Owner | Start Date | End Date | Status | Duration
Secure speakers | Event Manager | 2025-07-01 | 2025-07-02 | Not Started | 1
Set up registration page | Web Dev | 2025-07-03 | 2025-07-05 | Not Started | 2
Promote event | Marketing Team | 2025-07-06 | 2025-07-19 | Not Started | 13
Conduct dry run | Technical Lead | 2025-07-20 | 2025-07-24 | Not Started | 4
Host event | Host | 2025-07-25 | 2025-07-25 | Not Started | 0